## Work Plan
DEVOPS BOOTCAMP
PROJECT SIMULATION WORKPLAN
DAY | Activities | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Percent Complete | Status | Comments
1 | Requirements Analysis and Planning
| Role Deployment | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed | Team Lead/CI-CD: Angelo Q. De Rivera CI-CD: Patrick Ian A. Limpin Dev/CI-CD: Rhodenel S. Omaña Document Writers: Bianca Denise A. Del Puerto Angela Lynne G. Lapus
| Identification and Dissemination of Tasks | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed
| Documenting Work Plan | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed
| Environment Setup (Cloud Formation) |  |  | 2016-07-14
Setup ADOP Gen5 Tools
| Jenkins | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed
| Sonarqube | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed
| Ansible | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed
| GitLab | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed
| Selenium | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed
| Setup Tomcat | 2016-07-14 | 2016-07-14 | 2016-07-14 | 2016-07-14 | 100 | Completed
Code Development
| Javascript Calculator | 2016-07-14 | 2016-07-22 | 2016-07-14 |  | 50 | In Progress
2 | CI-CD
Developer Check-in code to Repository
Configure GitLab and Jenkins
Configure Jenkins and Maven
3 | Configure Jenkins and Sonarqube
Deploy App from Ansible to Tomcat
Test app using Selenium
4 | Debugging
Debug Project Pipeline
Finalize Documents
| Prepared by: |  |  |  |  | Reviewed by:
| Patrick Ian A. Limpin | Rhodenel S. Omaña |  |  |  |  | Angelo Q. De Rivera
| CI-CD | Developer |  |  |  |  | Team Lead
| Angela Lynne G. Lapus | Bianca Denise A. Del Puerto
| Document Writer | Document Writer

## Activities Percentage
STAGES | ACTIVITIES | STATUS | PERCENTAGE PER ACTIVITY | OVERALL PERCENTAGE
Requirements Analysis and Planning | Role Deployment | 1 | 33.3333 | 66.6667
| Identification and Dissemination of Tasks | 1 | 33.3333
| Documenting Work Plan | 0 | 0
Environment Setup | Setup ADOP Gen5 Tools |  | 0 | 0
| Jenkins | 0 | 0
| Sonarqube | 0 | 0
| ELK | 0 | 0
| Sensu | 0 | 0
| Nexus | 0 | 0
| Ansible | 0 | 0
| GitLab | 0 | 0
| Selenium | 0 | 0
| Setup Tomcat | 0 | 0
OVERALL PERCENTAGE |  |  |  | 33.3333

## Roles
NAME | EID | ROLE
Angelo Q. De Rivera | angelo.q.de.rivera | Team Lead ¦ CI/CD
Patrick Ian A. Limpin | patrick.ian.a.limpin | CI/CD
Rhodenel S. Omaña | rhodenel.s.omana | Dev ¦ CI/CD
Bianca Denise A. Del Puerto | bianca.a.del.puerto | Document Writer
Angela Lynne G. Lapus | angela.lynne.g.lapus | Document Writer